## Incident report 1
BUG ID | 1
Project Name | Contoller
Module Name | Display
Level or phase | System Test
Defect Type | Nonfuctional
Severity | Low
Priority
Summary | Verify if on LCD is displayed the message:" Incorrect Password!" when you enter a wrong password
Description | Step1: Turn on the controller Step2: Read the LCD Step3: Enter an incorrect pasword 89#*
Expected behavior | The LCD should display: Incorrect Password!
Observed behavior | The LCD display: "Incorrect !". The word "Password" is missing
Test case name | Incorrect Password Message
Test case ID | 4
Req ID | 3
Status | Open

## Incident report 2
BUG ID | 2
Project Name | Contoller
Module Name | Display
Level or phase | System Test
Defect Type | Functional
Severity | Medium
Priority
Summary | Verify an incorrect pasword consist of three digits
Description | Step1: Turn on the controller Step2: Read the LCD Step3: Enter an incorrect pasword consist of three digits: 235
Expected behavior | The LCD should display: Incorrect Password!
Observed behavior | The LCD screen does not display the message: Incorrect Pasword!
Test case name | Incorrect Password less than four digit
Test case ID | 5
Req ID | 2, 3, 4
Status | Open

## Incident report 3
BUG ID | 3
Project Name | Contoller
Module Name | Display
Level or phase | System Test
Defect Type | Nonfuctional
Severity | Low
Priority
Summary | Verify an incorrect pasword consist of four digits
Description | Step1: Turn on the controller Step2: Read the LCD Step3: Enter an incorrect pasword consist of four digits: 4568
Expected behavior | The LCD should display: Incorrect Password!
Observed behavior | The LCD display: "Incorrect !". The word "Password" is missing
Test case name | Incorrect four digit Password
Test case ID | 6
Req ID | 2, 3, 4
Status | Open

## Incident report 4
BUG ID | 4
Project Name | Contoller
Module Name | Display
Level or phase | System Test
Defect Type | Nonfuctional
Severity | Low
Priority
Summary | Verify an incorrect pasword consist of five digits
Description | Step1: Turn on the controller Step2: Read the LCD Step3: Enter an incorrect pasword consist of five digits: 45892
Expected behavior | The LCD should display: Incorrect Password!
Observed behavior | The LCD display: "Incorrect !". The word "Password" is missing
Test case name | Incorrect Password greater than four digit
Test case ID | 7
Req ID | 2, 3, 4
Status | Open

## Incident report 5
BUG ID | 5
Project Name | Contoller
Module Name | Display
Level or phase | System Test
Defect Type | Nonfuctional
Severity | Low
Priority
Summary | Verify an incorrect pasword consist of digits and letters
Description | Step1: Turn on the controller Step2: Read the LCD Step3: Enter an incorrect pasword consist of digits and letters: 58AM9
Expected behavior | The LCD should display: Incorrect Password!
Observed behavior | The LCD display: "Incorrect !". The word "Password" is missing
Test case name | Incorrect Password consisting of numbers and letters
Test case ID | 8
Req ID | 2, 3, 4
Status | Open

## Incident report 6
BUG ID | 6
Project Name | Contoller
Module Name | Display
Level or phase | System Test
Defect Type | Nonfuctional
Severity | Low
Priority
Summary | Verify an incorrect pasword consist four letters
Description | Step1: Turn on the controller Step2: Read the LCD Step3: Enter an incorrect pasword consist of four letters: SISI
Expected behavior | The LCD should display: Incorrect Password!
Observed behavior | The LCD display: "Incorrect !". The word "Password" is missing
Test case name | Incorrect Password consisting of letters
Test case ID | 9
Req ID | 2, 3, 4
Status | Open

## Incident report 7
BUG ID | 7
Project Name | Contoller
Module Name | Display
Level or phase | System Test
Defect Type | Functional
Severity | High
Priority
Summary | Check if we can set a new password
Description | Step1: Turn on the controller Step2: Read the LCD Step3: Set a new pasword
Expected behavior | The LCD should display: Set a new password
Observed behavior | The LCD screen does not display the message: Set a new password
Test case name | Set a new Password
Test case ID | 10
Req ID | 4
Status | Open

## Incident report 8
BUG ID | 8
Project Name | Contoller
Module Name | Display
Level or phase | System Test
Defect Type | Functional
Severity | Medium
Priority
Summary | Check if the led lights up when the correct password is entered
Description | Step1: Turn on the controller Step2: Read the LCD Step3: Enter the correct password: 1234
Expected behavior | The Led should lights up only when correct password is entered
Observed behavior | The Led lights up until the correct password is enetered
Test case name | The lighting up of the led
Test case ID | 11
Req ID | 5
Status | Open

## Incident report 9
BUG ID | 9
Project Name | Contoller
Module Name | Display
Level or phase | System Test
Defect Type | Functional
Severity | Medium
Priority
Summary | Check if the LED is off for the entire duration of the program, except for the case when the correct pasword is entered
Description | Step1: Turn on the controller Step2: Read the LCD Step3: Enter the correct password: 1234
Expected behavior | The Led should be turned off
Observed behavior | The Led lights up when the controller is turn on until the password entered is correct
Test case name | The Led Function
Test case ID | 12
Req ID | 6
Status | Open

## Incident report 10
BUG ID | 10
Project Name | Contoller
Module Name | Display
Level or phase | System Test
Defect Type | Nonfunctional
Severity | Low
Priority
Summary | Verify if on LCD is displayed the message:" WELCOME BACK MASTER!" when you enter the correct password
Description | Step1: Turn on the controller Step2: Read the LCD Step3: Enter the correct password: 1234
Expected behavior | The message: WELCOME BACK MASTER! must appear on LCD if the password is correct
Observed behavior | The LCD screen display the message: WELCOME BACK MASTER. The carachter "!" is missing
Test case name | Welcome Message
Test case ID | 13
Req ID | 7
Status | Open

## Incident report 11
BUG ID | 11
Project Name | Contoller
Module Name | Display
Level or phase | System Test
Defect Type | Functional
Severity | Medium
Priority
Summary | Verify if after the message: Welcome back Master is a delay of 3000 ms
Description | Step1:Turn on the controller Step2: Read the LCD Step3: Enter the correct password: 1234 Step4: Verify if is a delay of 3000 ms after the welcome message
Expected behavior | The delay has to be: 3000 ms
Observed behavior | The delay has to be: 3000 ms - False - the delay is 2000 ms (line 116: delay(2000)) The variable mode = 3 - True (line 117: mode = 3)
Test case name | Delay 3000 ms
Test case ID | 14
Req ID | 8
Status | Open

## Incident report 12
BUG ID | 12
Project Name | Contoller
Module Name | Display
Level or phase | System Test
Defect Type | Functional
Severity | Medium
Priority
Summary | Verify if the message Locked appears when we press the key "#" or "*"
Description | Step1:Turn on the controller Step2: Read the LCD Step3: Enter the correct password: 1234 Step4: Press the key "#" or "*"
Expected behavior | The message: Locked must appear on LCD
Observed behavior | The LCD screen does not display the message: Locked The variable mode = 3 - True (line 61: mode = 3)
Test case name | The message Locked
Test case ID | 16
Req ID | 9
Status | Open